October 20, 2009

1:00 PM

CA Public Utilities Commission Office – San Francisco

505 Van Ness Avenue, Room 3212

San Francisco, CA 94102

Present (Committee):

- Marci Evans (Cox Communications) – Alternate

- Michele King (Division of Ratepayer Advocates) - Alternate

- Ken McEldowney (Consumer Action)

- Jeff Mondon (AT&T)

- Charlie Toledo (Suscol Intertribal Council)

- Mike Gipson (Community Action Board of LA)

Present (CPUC Staff):

- Benjamin Schein (LifeLine Implementation Project Manager)

- Jonathan Lakritz (Communications Division Manager)

- Richard Maniscalco (Communications Division Analyst)

- Patti Long (CAB)

- Maria Ramirez (Fiscal)

- Benson Jung (Fiscal)

- Beverly Sligh (Fiscal)

- Kyle DeVine (TEAM)

Present (Public):

- Taura O’Larisey (RHA)

- Barbara Rosenberg (Solix)

- Jack Donovan (Solix)

On Conference Line

- Julie Weigand (RHA)

- Michelle Vlyatt (RHA)

- Karen Haith (Solix)

- Gregory Davis (CAB)

- Introduction, Ken McEldowney, Chairperson

- Meeting was called to order at 1:06 pm.  Everyone present introduced themselves to the group.

- Approval of Minutes:

- Charlie Toledo moved to adopt the minutes.  Jeff Mondon seconded.  All members voted Aye.

- Contract Reports:

  - Solix presented the following information:

August Response Rates

Applications – 66.7%

Renewals – 78.3%

Renewal (Doc. Req.) – 68.7%

September Response Rtes

Applications – 45.8%

Renewals – 59.8%

Renewal (Doc. Req.) – 44.4%

Received Applications Due in August Approval Rates

Applications – 85.4%

Renewals – 97.0%

Renewal (Doc. Req.) – 54.3%

Received Applications Due in September Approval Rates

Applications – 87.2%

Renewals – 97.0%

Renewal (Doc. Req.) – 49.8%

Language Response Rates for September:

| English | Application | 65.4% |
| --- | --- | --- |
|  | Renewals | 72.5% |
|  | Renewal (Doc. Req.) | 61.2% |
| Spanish | Application | 67.5% |
|  | Renewals | 68.8% |
|  | Renewal (Doc. Req.) | 58.9% |
| Chinese | Application | 84.2% |
|  | Renewals | 75.4% |
|  | Renewal (Doc. Req.) | 64.0% |
| Korean | Application | 76.2% |
|  | Renewals | 69.4% |
|  | Renewal (Doc. Req.) | 63.2% |
| Japanese | Application | 90.9% |
|  | Renewals | 78.0% |
|  | Renewal (Doc. Req.) | 80.0% |
| Vietnamese | Application | 84.8% |
|  | Renewals | 69.3% |
|  | Renewal (Doc. Req.) | 67.4% |
| Tagalong | Application | 70.5% |
|  | Renewals | 82.3% |
|  | Renewal (Doc. Req.) | 92.9% |

- According to Solix, these numbers are fairly consistent.

  - RHA/Michaela presented information related to their Marketing/Outreach program

- RHA is starting work on an educational video

- Phase 1 media buy ended the previous week

- RHA is developing 2 Public Service Announcements

- RHA continues to participate in statewide events and presenting to community partners

  - Michaela presented information related to their Call Center

- Call volume for August/September is about 5,200 calls

- Call volume is down, in part due to an effort to move callers to carriers (no way to track)

  - TEAM distributed a one-page handout and discussed their work

- Their work derives from the LEP (Limited English Proficiency) decision and work with 33 CBOs statewide

- They have a $1.9 million annual budget

- They do a great deal of work assisting recent immigrants, and are not solely focused on the LifeLine program

- TEAM members tell them about LifeLine, and assist them in applying to the program

- They also assist with appeals and complaints

- Kyle DeVine will provide numbers of customers who applied and were denied for non-compliance.  In addition, if she can provide individual customer numbers, the CPUC and CAB can research the cases to determine if there is a problem

- It was recommended that they look into coordinating with Catholic charities in the southern California area, as well as the LifeLine Marketing contractor

- Fiscal Report:

- Fiscal passed out copies of the most recent LifeLine budget report

  - Information on the sheet was explained, and Fiscal now shows where the $45 million loan to the General Fund is located

  - There is a pending question with Fiscal as to the proper funding year to pay out contract costs

- CAB Report:

- No report, as the new database system is still being developed.

- Patti Long noted that all older cases are resolved, and that CAB is current on all appeals, with a few pending carrier complaints.

  - No English/Spanish backlog, although there are 32 pending cases in Asian languages that are delayed due to translation requirements

    - Most cases are within 60 days except for the Vietnamese language cases, which are within 90 days

  - The question was asked about getting informal assistance from carriers that assist in these languages

  - This item will be added to the regular agenda

- Staffing changes

  - The 2 year limited term employees are scheduled to disappear in November

- ULTS Budget – 2010/11

- Due to uncertainties related to the draft decision, the budget resolution was put on hold for now

- Internally, CD staff is reviewing different scenarios to determine the most likely budget affect of various assumptions from the PPP OIR

- Deadlines include the governor’s proposed budget in January, and the price deregulation in January 2011.

- Legal Liaison:

- According to Sindy Yun, there is no update on the Conflict of Interest Issue.

  - Commission has signed off on the proposed legislation.

  - We sought a sponsor, but were unable to obtain one.

  - Commission intends to reintroduce the proposed legislation in 2009.

  - There is no further action on this issue at this time.

- AB 1528 (Ruskin) would freeze rates paid by LifeLine customers and require a determination by the CPUC that wireless providers provide an equal quality service as landline before they could participate in the LifeLine program

  - There is no further action on this issue at this time, although it can be raised again in the next legislative cycle.

- Public Comments:

- LifeLine Awareness Week was discussed, and it was noted that as of yet, there has been no noticeable effect on LifeLine customer counts (applied or pending)

- The issue was raised again about carriers not providing correct information about Enhanced (Tribal) LifeLine

  - It was requested that any instances of customers being given false information be provided to the CPUC for investigation

  - This item will be added as a regular agenda item until it is resolved

- Communications Division Liaison reports:

  - CD staff updates the Committee on the Solix contract

  - Update on the Implementation Group and other process improvements

  - Update on the Public Programs OIR.

  - Report on upcoming items.

- Benjamin Schein reported on the steps being taken by Solix, the carriers, and the Commission through the Implementation Group meetings held every two weeks.  Commission staff also has a conference call with Solix staff every week.

  - Solix contract

    - The contract is set to expire on June 30, 2010.

    - CD will be sending the contract out to bid (by standard RFP rules) within the next few months.

  - Solix process improvements

    - In response to concerns raised about carriers not providing accurate Tribal LifeLine information, the Commission is working on changing the standard forms to include a self-certifying option for people who live on tribal land.  An eligible applicant can simply fill in a bubble and receive Tribal LifeLine benefits

    - AT&T noted that a process change involving new data from Solix would require several months lead time to give their IT staff enough time to make the necessary changes

  - Other languages

    - The Commission is also working with carriers to determine what languages are supported with an eye towards possibly expanding the list of languages supported by LifeLine.  In addition to the currently supported languages, AT&T supports Russian and Polish, ConnectTo supports Russian and Armenian.

  - Customer counts

    - In response to a request from DRA, CD will be posting LifeLine customer counts by carrier on our website.

  - PPP OIR

    - The draft decision is on hold

  - Rate increases

    - AT&T has announced (and has begun informing their customers) that their basic rate will increase effective January 2, 2010.  Basic flat rate will increase $2.95, and the LifeLine rate will increase by $0.73 (flat) and $0.39 (measured).

- ULTS-AC Annual Report – Status:

    - Ken McEldowney has been working on the report, and submitted it to the AC for review

    - Members are asked to submit any proposed changes to Benjamin within one month, so that Ken McEldowney has enough time to incorporate them

- ULTS-AC Report:

  - Recommendations for CPUC staff

  - Proposed initiatives for 2008/2009

    - Staff was complemented for being responsive to the needs of the committee

    - A number of items were requested to be added to the Agenda, including CAB’s in-language backlog, the proposal to add languages to LifeLine, and the issue of problems faced by Tribal customers

- Review of Administrative Committee vacancy status:

  - Invitation to fill Small ILEC and CBO vacancy

  - Invitation to nominate Alternates

    - Information on adding a CBO representative is pending on Ana Montes

      - Charlie Toledo intends to recommend an Alternate for her position.

- Future Meeting Date/Location:

    - It was decided to hold the next meeting in San Francisco on Thursday, December 10th at 1:00 pm PST.

- Adjournment:

- Charlie Toledo moved, Mike Gipson seconded, and all voted Aye.

- The meeting was adjourned at 2:30 pm.

These locations are accessible to people with disabilities.  If specialized accommodations for the disabled are needed at any of the locations of this meeting, e.g., sign language interpreters please call the PUC Public Advisor at (415) 703-2074 // email:  public.advisor@cpuc.ca.gov three business days in advance of the meeting.  Meeting location where accommodations are required should be specified.